## Project Plan
Capstone Project Group E - Project Plan
[6 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7
[6 empty] | 7 Mar - 13 Mar | [6 empty] | 14 Mar - 20 Mar | [6 empty] | 21 Mar - 27 Mar | [6 empty] | 28 Mar - 3 Apr | [6 empty] | 4 Apr - 10 Apr | [6 empty] | 11 Apr - 17 Apr | [6 empty] | 18 Apr - 24 Apr
TASK | ASSIGNED TO | Planned in Week | PROGRESS | START | END | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Team Introduction | Team | Week 1 | Complete | 2022-03-06 | 2022-03-06
Selection of Project Tools | Team | Week 1 | Complete | 2022-03-07 | 2022-03-13
Set up MS Teams | David | Week 1 | Complete
Set Up Project Planner | Shuba | Week 1 | Complete
Minutes of meeting | Team | Week 1 | Complete
Team Member Roles | Team | Week 1 | Complete | 2022-03-07 | 2022-03-13
Project Implementation Checklist |  | Week 1 | In Progress | 2022-03-07 | 2022-03-13
Project Gantt Chart | Shuba | Week 1 | In Progress | 2022-03-07 | 2022-03-13
Project Plan Report Template | Shuba, Jamie | Week 1 | Complete | 2022-03-07 | 2022-03-13
Project Plan Report Contents | David, Abdul,Jamie | Week 1 | In Progress | 2022-03-09 | 2022-03-14
Set up GitHub - Forked from the UNSW Project | Shuba, Chris | Week 1 | Complete | 2022-03-12 | 2022-03-13
Project Plan Submission | Jamie | Week 1 | In Progress | 2022-03-07 | 2022-03-13
Week 2 - Meeting Agenda | Shuba , Sonal | Week 2 | Complete | 2022-03-13 | 2022-03-14
Data Exploration |  | Week 2
Research |  | Week 2
Finalize Articles for Project
Review Data Analytics Techniques
Finalize Statistical Tools
Perform Dimensionality Reduction
Develop Machine Learning Algorithms
Data Analysis
Machine Learning
Structuring of Report
Develop Visualization
Prepare Group Project Report
Prepare Presentation Video