## Project Plan
Capstone Project Group E - Project Plan
[6 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7
[6 empty] | 7 Mar - 13 Mar | [6 empty] | 14 Mar - 20 Mar | [6 empty] | 21 Mar - 27 Mar | [6 empty] | 28 Mar - 3 Apr | [6 empty] | 4 Apr - 10 Apr | [6 empty] | 11 Apr - 17 Apr | [6 empty] | 18 Apr - 24 Apr
TASK | ASSIGNED TO | Planned in Week | PROGRESS | START | END | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Team Introduction | Team | Week 1 | Complete | 2022-03-06 | 2022-03-06
Selection of Project Tools | Team | Week 1 | In Progress | 2022-03-07 | 2022-03-13
Set up MS Teams | David | Week 1 | Complete
Set Up Project Planner | Shuba | Week 1 | Complete
Minutes of meeting | Abdul | Week 1 | Complete
Team Member Roles |  | Week 1 | In Progress | 2022-03-07 | 2022-03-13
Project Implementation Checklist |  | Week 1 | In Progress | 2022-03-07 | 2022-03-13
Project Plan Submission | Team | Week 1 | In Progress | 2022-03-07 | 2022-03-13
Project Gantt Chart | Shuba | Week 1 | In Progress | 2022-03-07 | 2022-03-13
Project Plan Report Template | Shuba, Jamie | Week 1 | In Progress | 2022-03-07 | 2022-03-13
Project Plan Report Contents | Team | Week 1 | In Progress | 2022-03-09 | 2022-03-14
Data Exploration |  | Week 2
Research |  | Week 2
Finalize Articles for Project
Review Data Analytics Techniques
Finalize Statistical Tools
Perform Dimensionality Reduction
Develop Machine Learning Algorithms
Data Analysis
Machine Learning
Structuring of Report
Develop Visualization
Prepare Group Project Report
Prepare Presentation Video

## Roles
Details of the Roles Required for this Project
Role | Primary Responsibility | # of Team Members
Project Lead | To steer the project and coordinate with the team. Highlight red flags and keep track of tasks and activities. To create any missing Tasks and allocate the task to the team members. To update minutes of meeting and track action items. To be the point of contact for any queries regarding the team progress | 1
Data Scientists | To search literature used as a reference for the project. To Analyse the energy demand data To Evaluate different Forecast Models to be used. To Develop the Machine Learning Models. To execute the Models and compare if Forcast Matches with the Demand. | 2
Data Visualisation Specialists | To determine the Visualisation Tool used. Understand the Graphs which needs to be generated. Work on data visualisation tasks of the project. | 1
Communications Specialists | To update and prepare the final Reports. To sync final documents in Git Hub twice a week. Sync the final files in Git Hub every week. To Create Report / Other Templates, which the team will use. To own the Documents / Report Submissions. To make sure the documents are correctly updated. To create Videos and prepare them for final submission | 2
Please note: Each and every one of us are Data Scientists and have gone through
the same learning curve. This is the reason it is important to understand that we
should be able to work on any role within the team to fill the gaps as and when
the project demands.
In order to structure the project properly we need to define a set of roles.
These roles are defined based on specific set of activities required
to successfully deliver the project.
Each team member will have a specific role will have a set of primary responsibilities.
However, as we progress through the project we will be flexible enough to
work any tasks / activites which are outside the primary set of responsibilities
Note on D3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hi All, I have updated the Roles and Primary Responsibilities required for this project. Please review this. Here the total number of Team members are more than we have. That means some members of the Team need to play multiple roles. We need to discuss this further on Friday.

## Team Members with Assigned Role
Role Assignment
First Name | Last Name | ZID | Roles
Abdul | El-Hamawi | z5019165 | DS
Chris | Strods | z5329477 | viz
David | Anderson | z5343521 | DS
Jamie | Twiss | z5353394 | Comms
Shubhankar | Dutta | z5304573 | Comms, lead
Sonal | Chawla | z5092985 | comms, viz
* I have removed the roles as we need to discuss this on Friday's meeting
and then align ourselves with the defined roles and responsibilities.

## List of Tools to be Used
Software used for your group meetings
Project Application Category | Selected Software Tools | Justification
Project Management | GitHub (mandatory) | Had to select it as it was mandatory
List-making application | Task lists configures in Microsoft Teams ( Integrated MS Planner) | We configured Microsoft Teams Task list as it is very similat to MS Planner and is integrated with MS Teams which is used as a Collaborative Teams Platform
File sharing | Sharepoint linked with One Drive | We used Sharepoint as it is integrated with Microsoft Teams and Office 365
Collaborative editing - Documents | Office 365 MS Word | We used Office 356 MS Word to perform collaborative editing which was integrated with MS Teams
Collaborative editing - Programs | Google Colab | Using Google Collab multiple people can work and develop the machine learning model collaboratively
Organise Group meetings | Microsoft Teams | We used the UNSW microsoft teams which was integrated with our Office 365 UNSW Emails
Implementation Checklist
What software will you use for your group meetings? | Micosoft Teams
What Software is used for your group meetings | MS Teams Meetings
What software will you use to manage your work collaboratively? | MS Teams Task List (Integrated MS Planner) OneDrive, MS Teams, Office 365, GitHub
Justification of the software manage your work collaboratively? | As mentioned in the above table
What software will you use for data analysis? | Python, R/ RStudio, Tableau
What software you will use to write your group report in a reproducible manner? | Office 365 MS Word / R Markdown
Justification of the software used to write your group report in a reproducible manner? | ??
What software will you use for your oral presentation? | Powerpoint / Prezi along with Apple IMovie to edit videos